## Summary
Antelligence Feature Status Tracker
Canonical workbook | /Users/operator/antelligence-app/docs/antelligence-feature-status.xlsx
Last updated | 2026-06-22
Feature rows | 39
Tracked issues | 19
Current phase | All 39 user stories inventoried, tested, and fixed/retested where defects were found; no pending behavior, fix, or retest rows remain.
Source basis | Current worktree code inspection plus browser/API verification
Next loop | Use this workbook as the canonical regression tracker; add new Error Log and Test Runs rows for any future defects.
Do not fork | Update this workbook instead of creating alternate trackers
Status | Count | Formula | Notes
Inventoried | 17 | 17 | Rows mapped from code
Code Issue Candidate | 0 | 0 | Needs browser/build verification
Behavior Tests Pending | 0 | 0 | Next active phase
Fixes Pending | 0 | 0 | Only fix after verified error
Retests Pending | 0 | 0 | Required after fixes

## Feature Stories
ID | Area | Feature | User Story | Expected Behavior | Code Evidence | Priority | Feature Status | Behavior Test Status | Error Notes | Fix Status | Retest Status
APP-001 | Navigation | Intro landing and experience routing | As a visitor, I want to choose an Ant Colony, Tumor Nanobot, or Tumor Hunt experience from the first screen so I can enter the right simulator. | The intro page shows three primary buttons, Enter key starts Ant Colony, and tumor buttons route to /tumor and /tumor-hunt. | frontend/src/components/IntroPage.tsx; frontend/src/App.tsx | High | Inventoried | Tested - Pass | Browser retest: intro buttons render; Enter enters Ant Colony; Tumor and Tumor Hunt buttons route cleanly. | Not Applicable | Not Applicable
APP-002 | Navigation | Route handling and 404 | As a user, I want valid routes to load the right page and bad routes to show a useful fallback so I do not get a blank app. | Routes /, /comparison, /tumor, /tumor-hunt render their pages; all other routes render NotFound with a home link. | frontend/src/App.tsx; frontend/src/pages/NotFound.tsx | Medium | Fixed | Tested - Fail | 404 fallback rendered but logged a console error for normal missing-route navigation. | Fixed | Retested - Pass
APP-003 | Runtime | Preview mode guardrails | As a public-preview user, I want backend-only actions disabled with clear messaging so I do not expect unavailable local execution. | Preview banner appears when preview mode is enabled and run buttons show informational toasts instead of calling local backends. | frontend/src/components/PreviewModeBanner.tsx; frontend/src/lib/runtime.ts; frontend/src/pages/*.tsx | High | Inventoried | Tested - Pass | Preview-mode browser retest: banner/checkpoints rendered on Ant, Comparison, Tumor, and Hunt pages; all run buttons stayed idle and made no backend requests. | Not Applicable | Not Applicable
ANT-001 | Ant Colony | Habitat configuration | As a simulation user, I want to tune grid width, grid height, food resources, and colony size so I can test different foraging environments. | Sidebar sliders update config within visible bounds before a run. | frontend/src/components/SimulationSidebar.tsx | High | Fixed | Tested - Fail | Focused width slider changed value, but ArrowRight also advanced playback because global shortcuts did not ignore slider focus. | Fixed | Retested - Pass
ANT-002 | Ant Colony | Agent/model/prompt configuration | As a simulation user, I want to choose agent type, model, and prompt style so I can compare rule-based and LLM-driven behavior. | Agent type and model selects update config; prompt style supports Adaptive, Structured, and Autonomous. | frontend/src/components/SimulationSidebar.tsx | High | Inventoried | Tested - Pass | Browser retest: agent type changed to Rule-Based and run payload sent selected model/prompt values. | Not Applicable | Not Applicable
ANT-003 | Ant Colony | Queen coordination settings | As a simulation user, I want to enable a queen and optionally use an LLM queen so I can test coordination overhead and benefit. | Enable Queen switch controls visibility of LLM Queen switch and sends both values in run config. | frontend/src/components/SimulationSidebar.tsx; frontend/src/pages/Index.tsx | High | Inventoried | Tested - Pass | Browser retest: Queen enabled, LLM Queen disabled, request sent use_queen=true/use_llm_queen=false, and Queen report rendered. | Not Applicable | Not Applicable
ANT-004 | Ant Colony | Predator settings | As a simulation user, I want to enable predators and tune predator count/type/fear pheromone so I can test survival pressure. | Predator fields appear only when enabled; run config sends n_predators as zero when disabled. | frontend/src/components/SimulationSidebar.tsx; frontend/src/pages/Index.tsx | Medium | Fixed | Tested - Fail | Predator fields appeared and request sent Rule-Based predators, but helper copy still said Smart LLM decision making. | Fixed | Retested - Pass
ANT-005 | Ant Colony | Pheromone and step configuration | As a simulation user, I want to tune pheromone decay/deposits/max value and max steps so I can observe trail behavior and run length effects. | Pheromone fields are sent to backend; max steps slider controls loading total and simulation length. | frontend/src/components/SimulationSidebar.tsx; backend/main.py | High | Inventoried | Tested - Pass | Browser/network retest: /simulation/run payload included max_steps=50 and pheromone decay/deposit/max values; response produced pheromone chart data. | Not Applicable | Not Applicable
ANT-006 | Ant Colony | Run ant simulation | As a simulation user, I want to run the configured ant simulation and see a loading state, result grid, and metrics. | Run buttons POST /simulation/run unless preview mode is active; success stores results and shows playback; failure shows a toast error. | frontend/src/pages/Index.tsx; backend/main.py | Critical | Fixed | Tested - Fail | Verified UI run was blocked/noisy by CORS, blockchain latency, missing-key warning, and food count mismatch; fixed and retested Rule-Based happy path. | Fixed | Retested - Pass
ANT-007 | Ant Colony | Playback controls and keyboard shortcuts | As a simulation user, I want play, pause, step, replay, start/end, loop, speed, and keyboard shortcuts so I can inspect simulation behavior over time. | Controls are disabled until results exist; Space, arrows, Home, End, and R operate after a simulation is loaded; timeline slider changes the displayed step. | frontend/src/components/SimulationControls.tsx; frontend/src/pages/Index.tsx | High | Fixed | Tested - Fail | Timeline displayed inconsistent 0-based and 1-based step labels and had no real scrub control; slider now updates currentStep and labels align. | Fixed | Retested - Pass
ANT-008 | Ant Colony | Grid overlays and legend | As a simulation user, I want to toggle efficiency and pheromone overlays and read a legend so visual states are understandable. | Overlay buttons appear after simulation results; grid receives latest detailed pheromone/efficiency data; legend explains entities and maps. | frontend/src/pages/Index.tsx; frontend/src/components/SimulationGrid.tsx | Medium | Fixed | Tested - Fail | Overlay buttons and legend rendered, but the pheromone toggle always read Show Pheromone Maps even when maps were visible. | Fixed | Retested - Pass
ANT-009 | Ant Colony | Queen report | As a simulation user, I want to see queen reporting when queen coordination is enabled so I can inspect central recommendations. | Queen report renders only after simulation results and when use_queen is true. | frontend/src/pages/Index.tsx; frontend/src/components/QueenAntReport.tsx | Medium | Inventoried | Tested - Pass | Browser retest: Queen Ant Report rendered after Rule-Based queen run with heuristic guidance text and report metadata. | Not Applicable | Not Applicable
ANT-010 | Ant Colony | Performance analysis charts | As a simulation user, I want performance charts after a run so I can understand food depletion, API calls, and pheromone/efficiency behavior. | PerformanceCharts renders after results and receives food depletion, current metrics, pheromone data, and efficiency data. | frontend/src/pages/Index.tsx; frontend/src/components/PerformanceCharts.tsx | High | Fixed | Tested - Fail | Charts rendered, but hotspot and efficiency summary copy described LLM ant behavior during a Rule-Based run. | Fixed | Retested - Pass
ANT-011 | Ant Colony | Historical performance | As a returning user, I want recent run history, aggregate stats, export, and clear controls so I can compare repeated simulations. | History panel should show no-history state initially, then aggregate last 15 runs, export JSON, and clear history after confirmation. | frontend/src/components/HistoricalPerformance.tsx; frontend/src/lib/simulationHistory.ts | High | Fixed | Tested - Fail | HistoricalPerformance expected synchronous local history helpers but simulationHistory.ts returned async API shapes; fixed with localStorage history and same-tab update event. | Fixed | Retested - Pass
ANT-012 | Ant Colony | Blockchain analytics panel | As a simulation user, I want blockchain transaction analytics after runs that produce transaction data so provenance claims are visible but not overstated. | Panel renders only when simulationResults.blockchain_transactions exists and displays transaction metrics; transaction logging is opt-in so local Rule-Based runs stay fast. | frontend/src/pages/Index.tsx; frontend/src/components/BlockchainMetrics.tsx; backend/main.py | Medium | Fixed | Tested - Fail | Backend ignored blockchain_enabled and submitted food collection transactions during default UI runs; now default false and passed into the model. | Fixed | Retested - Pass
ANT-013 | Ant Colony | Queen comparison panel | As a simulation user, I want to compare queen vs no-queen performance for the current config so I can judge coordination benefit. | Run Queen Comparison POSTs /simulation/compare and displays summary cards, chart, and analysis. | frontend/src/components/ComparisonPanel.tsx; backend/main.py | High | Inventoried | Tested - Pass | Browser/network retest: /simulation/compare returned 15 no-queen vs 15 with-queen; summary cards, chart, and analysis rendered. | Not Applicable | Not Applicable
COMP-001 | Comparison Lab | Batch comparison parameter selection | As an analyst, I want to select food counts, ant counts, agent types, and iterations so I can create a batch experiment matrix. | Buttons toggle selected counts/types; iteration select updates total simulation count; empty food, ant, or agent selections disable run; config controls do not mutate during an active batch. | frontend/src/pages/SimulationComparison.tsx | High | Fixed | Tested - Fail | Start was not disabled when agentTypes was empty, and config controls remained mutable during runs. | Fixed | Retested - Pass
COMP-002 | Comparison Lab | Batch comparison execution | As an analyst, I want to run all selected comparison combinations with progress feedback so I can gather comparative metrics. | Start Comparison loops through selected configs, POSTs /simulation/run with local-fast defaults, updates progress/results, and shows per-run failures. | frontend/src/pages/SimulationComparison.tsx; backend/main.py | High | Fixed | Tested - Fail | Comparison sent blockchain_enabled=true, causing slow real transaction logging even for Rule-Based one-run batches. | Fixed | Retested - Pass
COMP-003 | Comparison Lab | Comparison charts, table, and CSV export | As an analyst, I want charts, a detailed table, and CSV export after batch runs so I can review and share experiment outcomes. | After results exist, charts and table render; Export CSV downloads timestamped CSV with the visible results. | frontend/src/pages/SimulationComparison.tsx | Medium | Inventoried | Tested - Pass | Browser retest: charts and table rendered one result; CSV export generated simulation-comparison timestamped file and expected row. | Not Applicable | Not Applicable
TUMOR-001 | Tumor Simulation | Domain setup | As a tumor simulation user, I want to configure domain size, voxel size, and tumor radius so I can model different microenvironments. | Domain accordion exposes numeric inputs with min/max/step attributes and updates config. | frontend/src/components/TumorSimulationSidebar.tsx | High | Inventoried | Tested - Pass | Browser/network retest: Domain inputs exposed min/max/step; Domain Size keyboard increment changed 600->650 and request sent domain_size=650. | Not Applicable | Not Applicable
TUMOR-002 | Tumor Simulation | Nanobot model setup | As a tumor simulation user, I want to configure nanobot count, agent type, and model so I can compare nanobot control policies. | Nanobot accordion exposes number input, agent select, and model select when non-rule-based. | frontend/src/components/TumorSimulationSidebar.tsx | High | Inventoried | Tested - Pass | Browser retest: nanobot count input rendered; agent switched LLM-Powered->Rule-Based; model combobox hid for Rule-Based. | Not Applicable | Not Applicable
TUMOR-003 | Tumor Simulation | Queen coordination setup | As a tumor simulation user, I want to enable queen coordination and LLM queen behavior so I can test swarm guidance. | Queen accordion controls use_queen and conditionally exposes use_llm_queen. | frontend/src/components/TumorSimulationSidebar.tsx | Medium | Fixed | Tested - Fail | LLM Queen control hid when Queen was disabled, but hidden use_llm_queen still submitted true. | Fixed | Retested - Pass
TUMOR-004 | Tumor Simulation | Advanced simulation settings | As a tumor simulation user, I want to tune max steps, cell density, and vessel density so I can change simulation scale and biology. | Advanced accordion exposes numeric inputs that update config before run. | frontend/src/components/TumorSimulationSidebar.tsx | Medium | Inventoried | Tested - Pass | Browser/network retest: max steps, cell density, and vessel density inputs rendered with min/max/step and request sent max_steps=200, cell_density=0.001, vessel_density=0.01. | Not Applicable | Not Applicable
TUMOR-005 | Tumor Simulation | Run tumor simulation | As a tumor simulation user, I want to run the configured glioblastoma simulation and see loading, results, and stored session state. | Run POSTs /simulation/tumor/run unless preview mode; success shows playback; sessionStorage caching is best-effort and must not fail the completed run. | frontend/src/pages/TumorSimulation.tsx; backend/main.py | Critical | Fixed | Tested - Fail | Large tumor result payload exceeded sessionStorage quota and was treated as a simulation failure. | Fixed | Retested - Pass
TUMOR-006 | Tumor Simulation | Tumor playback controls | As a tumor simulation user, I want to play, pause, step, reset, jump start/end, set speed, and scrub progress so I can inspect treatment evolution. | Buttons update current step/play state; progress slider changes current step, pauses playback, and persists the selected step. | frontend/src/components/TumorSimulationControls.tsx; frontend/src/pages/TumorSimulation.tsx | High | Fixed | Tested - Fail | Progress slider had an onValueChange comment saying it was visual only and did not update parent currentStep. | Fixed | Retested - Pass
TUMOR-007 | Tumor Simulation | Substrate tabs and detail mode | As a tumor simulation user, I want to switch substrate maps and simple/detailed rendering so I can inspect biological signals. | Tabs switch selected substrate among oxygen, drug, IFN-gamma, TNF-alpha, perforin, chemokine; mode buttons toggle detailed rendering. | frontend/src/pages/TumorSimulation.tsx; frontend/src/components/TumorSimulationGrid.tsx | High | Inventoried | Tested - Pass | Browser retest after tumor run: Simple/Detailed controls and Oxygen, Drug, IFN, TNF, Perforin, Chemokine substrate tabs rendered; Detailed and Chemokine clicks produced 0 console warnings/errors. | Not Applicable | Not Applicable
TUMOR-008 | Tumor Simulation | Tumor visualization legend | As a tumor simulation user, I want a legend after results so I can interpret nanobots, tumor cells, vessels, and hypoxic regions. | Legend renders after simulation results and uses consistent visual labels. | frontend/src/pages/TumorSimulation.tsx | Low | Inventoried | Tested - Pass | Browser retest: Visualization Legend rendered after results with Nanobots, Tumor Cells, Blood Vessels, and Hypoxic Regions. | Not Applicable | Not Applicable
HUNT-001 | Tumor Hunt | Hunt configuration | As a hunt user, I want to configure agent type/model, nanobots, waves, cell counts, kill threshold, and pheromone overlay so I can run wave-based hunts. | Configuration panel updates HuntConfig; model select appears for non-rule-based agents; pheromone checkbox toggles overlay; copy does not imply LLM-only behavior when Rule-Based is selected. | frontend/src/pages/TumorHunt.tsx | High | Fixed | Tested - Fail | Header copy said LLM-brained nanobots even though the default and tested path is Rule-Based. | Fixed | Retested - Pass
HUNT-002 | Tumor Hunt | Run hunt simulation | As a hunt user, I want to run the wave-based hunt and see progress/errors so I can evaluate eradication behavior. | Run Hunt POSTs /simulation/tumor/hunt with 300s timeout; loading progress is shown; errors render in the config card. | frontend/src/pages/TumorHunt.tsx; backend/main.py | Critical | Inventoried | Tested - Pass | Browser/backend retest: default Rule-Based hunt completed with 34/34 cells killed and no console warnings/errors. | Not Applicable | Not Applicable
HUNT-003 | Tumor Hunt | Wave notifications and live stats | As a hunt user, I want wave arrival alerts and live stats so I can understand dynamic tumor spawning. | Wave notification appears when live cell count rises; stats show alive/killed cells, waves, drug, efficiency, and nanobot states. | frontend/src/pages/TumorHunt.tsx | High | Inventoried | Tested - Pass | Browser retest showed Wave 4 notification plus live stats for alive/killed cells, drug delivered, efficiency, and nanobot state counts. | Not Applicable | Not Applicable
HUNT-004 | Tumor Hunt | Hunt playback and scrubber | As a hunt user, I want playback buttons and a step scrubber so I can inspect each hunt step after results. | Buttons jump start/back/play/forward/end; range input changes currentStep and pauses playback. | frontend/src/pages/TumorHunt.tsx | High | Inventoried | Tested - Pass | Browser retest: autoplay reached final summary, scrubber moved from 107/107 to 54/107 and paused. | Not Applicable | Not Applicable
API-001 | Backend | Health and quick test endpoints | As an operator, I want health and quick-test endpoints so I can verify the backend is alive and simulation basics work. | GET /health, GET /test, POST /simulation/test, and GET /simulation/tumor/test return structured status/test payloads. | backend/main.py; backend/api_server.py | High | Fixed | Tested - Fail | backend.main import failed before sys.path included backend/ because litellm_client was imported too early; import order fixed. | Fixed | Retested - Pass
API-002 | Backend | Ant simulation endpoints | As the frontend, I need ant simulation, comparison, and performance endpoints so ant UI workflows have executable backing. | POST /simulation/run, /simulation/compare, and /simulation/performance accept schema configs and return structured results. | backend/main.py; backend/schemas.py | Critical | Fixed | Tested - Fail | CORS missing 127.0.0.1:8081 and metrics double-counted food after pickup/dropoff; both fixed and retested. | Fixed | Retested - Pass
API-003 | Backend | Tumor simulation endpoints | As the frontend, I need tumor simulation, hunt, strategy comparison, and CED comparison endpoints so medical workflows have executable backing. | POST /simulation/tumor/run, /performance, /compare, /hunt, and /compare-ced return structured or JSON results. | backend/main.py; backend/schemas.py | Critical | Fixed | Tested - Fail | Tumor quick-test and strategy endpoints worked, but Rule-Based runs logged IO_SECRET_KEY missing even though no LLM path was active. | Fixed | Retested - Pass
API-004 | Backend | Simulation cache/history endpoints | As a user, I want runs cached and comparable later so history features are persistent beyond the current component. | POST /simulation/cache, GET /simulation/history, and GET /simulation/compare/{id1}/{id2} manage cached_simulations in memory. | backend/main.py; frontend/src/lib/simulationHistory.ts | Medium | Inventoried | Tested - Pass | Live HTTP retest: cached ant/tumor payloads, history returned both, type filter returned tumor only, compare returned side-by-side metrics and differences. | Not Applicable | Not Applicable
API-005 | Backend | Packaged API server endpoints | As an integrator, I want the packaged antelligence-api entrypoint to run the documented durable API so CLI/local integrations can store and retrieve runs. | backend/api_server.py exposes /health, /simulate, and /runs/{run_id} with SQLite run storage. | backend/api_server.py; README.md; pyproject.toml | Medium | Fixed | Tested - Fail | Documented uv-run entrypoints were unavailable because uv packaging was disabled, and basic API runs defaulted to LLM mode. | Fixed | Retested - Pass
CLI-001 | CLI | Single simulation CLI | As an operator, I want to run one simulation from the terminal and optionally write JSON so I can reproduce runs outside the UI. | antelligence simulate accepts --steps, --bots, --grid-size, --seed, --output and writes config/metrics JSON. | backend/cli.py; README.md; pyproject.toml | Medium | Fixed | Tested - Fail | uv run antelligence could not spawn, and the module-path simulate command emitted an irrelevant IO_SECRET_KEY warning. | Fixed | Retested - Pass
CLI-002 | CLI | Benchmark CLI | As an operator, I want to run repeated simulations and aggregate kill-rate stats so I can compare parameter choices quickly. | antelligence benchmark accepts --runs, --steps, --bots, --grid-size, --output and returns summary/results. | backend/cli.py; pyproject.toml | Medium | Fixed | Tested - Fail | uv run antelligence could not spawn, and benchmark runs emitted irrelevant IO_SECRET_KEY warnings. | Fixed | Retested - Pass
CLI-003 | CLI | Leaderboard CLI | As an operator, I want to read the on-chain leaderboard with an offline fallback so blockchain availability does not crash the CLI. | antelligence leaderboard accepts --limit and prints leaderboard table or offline fallback message. | backend/cli.py; backend/chain/leaderboard.py; pyproject.toml | Low | Fixed | Tested - Fail | uv run antelligence could not spawn the documented leaderboard command before packaging was enabled. | Fixed | Retested - Pass

## Error Log
Issue ID | Feature ID | Issue Type | Observed From Code | Evidence | Verification Status | Fix Status
ISS-001 | ANT-011 | Runtime crash | HistoricalPerformance calls getAggregatedStats/getSimulationCount/exportHistoryAsJSON/clearSimulationHistory synchronously, but simulationHistory.ts exported async API-backed helpers with different return shapes. | frontend/src/components/HistoricalPerformance.tsx; frontend/src/lib/simulationHistory.ts | Verified in browser: stats.map is not a function | Fixed; retested pass
ISS-002 | TUMOR-006 | Non-functional progress scrubber | TumorSimulationControls slider had no parent update handler and onValueChange was intentionally a no-op. | frontend/src/components/TumorSimulationControls.tsx; frontend/src/pages/TumorSimulation.tsx | Verified from code and browser retest | Fixed; slider retested to Step 101/200
ISS-003 | APP-003 | CORS port coverage | Vite frontend runs on port 8081, while backend/main.py CORS origins included 8080 and 5173 but not 8081. | frontend/package.json; backend/main.py | Verified by failed OPTIONS preflight from http://127.0.0.1:8081 | Fixed; preflight retested 200 OK
ISS-004 | APP-001 | Lint warning cluster | npm --prefix frontend run lint passes with warnings: IntroPage missing handleEnter hook dependency, TumorSimulationGrid missing nanobotTrails hook dependency, and shadcn UI files trigger fast-refresh export warnings. | frontend/src/components/IntroPage.tsx; frontend/src/components/TumorSimulationGrid.tsx; frontend/src/components/ui/*.tsx | Verified warning | Pending
ISS-005 | ANT-012 | Slow default UI run | Backend ignored blockchain_enabled and initialized real food collection transaction logging even when the frontend intended a local-only run. | backend/schemas.py; backend/main.py; backend/simulation.py; frontend/src/components/SimulationSidebar.tsx | Verified in backend logs and browser hang/slow run | Fixed; retested with 0 blockchain transactions
ISS-006 | ANT-006 | Incorrect food metric | Food collection was counted once at pickup and again at nest dropoff, causing final food_collected to exceed the initial food count. | backend/simulation.py | Verified by API result: 25 collected with 15 initial food | Fixed; retested 15 collected with 15 initial food
ISS-007 | ANT-007 | Timeline labeling and scrub control | Ant simulation used zero-based currentStep in visible counters and rendered progress as a non-interactive bar. | frontend/src/components/SimulationControls.tsx; frontend/src/pages/Index.tsx | Verified in browser: Step card showed 0 / 13 while title showed Step 1 of 13 | Fixed; retested slider click moves to Step 7 of 13
ISS-008 | ANT-006 | Misleading Rule-Based console warning | Rule-Based runs emitted IO_SECRET_KEY missing warnings even though no LLM client was needed. | backend/simulation.py; frontend/src/pages/Index.tsx | Verified by browser console/backend logs | Fixed; fresh browser retest has 0 warnings
ISS-009 | TUMOR-005 | Session storage quota failure | Tumor simulation wrote the full result payload to sessionStorage inside the API success path; QuotaExceededError was caught as a failed simulation. | frontend/src/pages/TumorSimulation.tsx | Verified in browser console after successful tumor run | Fixed; storage is best-effort and retest has 0 warnings/errors
ISS-010 | COMP-002 | Slow comparison execution | Comparison Lab sent blockchain_enabled=true for every /simulation/run request, causing local Rule-Based batches to wait on real transaction logging. | frontend/src/pages/SimulationComparison.tsx; backend logs | Verified by backend log: blockchain_enabled true and multi-second food transaction writes | Fixed; retested one-run batch with 0 blockchain transactions
ISS-011 | COMP-001 | Incomplete run guard | Start Comparison only checked foodCounts and antCounts, so an empty agentTypes selection could produce a zero-run batch. | frontend/src/pages/SimulationComparison.tsx | Verified in browser after deselecting all agent types | Fixed; retested Start disabled when agentTypes is empty
ISS-012 | APP-002 | 404 console noise | NotFound logged normal missing-route fallback navigation as console.error, polluting browser error checks. | frontend/src/pages/NotFound.tsx | Verified in browser console on /definitely-missing-route | Fixed; retested 404 with 0 console warnings/errors
ISS-013 | HUNT-001 | Misleading mode copy | Tumor Hunt header described LLM-brained nanobots even when the default selected agent type was Rule-Based. | frontend/src/pages/TumorHunt.tsx | Verified in browser before fix | Fixed; retested copy now says Nanobot swarms
ISS-014 | ANT-004; ANT-008; ANT-010 | Misleading Ant UI copy/state | Ant predator helper text and performance chart copy implied LLM behavior during a Rule-Based run, and the pheromone overlay button did not expose the active Hide/Show state. | frontend/src/components/SimulationSidebar.tsx; frontend/src/components/PerformanceCharts.tsx; frontend/src/pages/Index.tsx | Verified in browser after predator-enabled Rule-Based run | Fixed; retested copy and toggle label
ISS-015 | ANT-001 | Keyboard shortcut collision | Global playback ArrowRight handled key events from a focused Radix slider, so changing a sidebar slider also advanced simulation playback. | frontend/src/pages/Index.tsx | Verified in browser: width changed 15->16 and step advanced 1/18->2/18 before fix | Fixed; retested width changed 16->17 while step stayed 2/18
ISS-016 | TUMOR-003 | Hidden stale Queen setting | Disabling Tumor Queen hid the LLM Queen switch but preserved use_llm_queen=true in the submitted run config. | frontend/src/components/TumorSimulationSidebar.tsx | Verified in /simulation/tumor/run request body | Fixed; retested request sends use_queen=false and use_llm_queen=false
ISS-017 | API-003 | Misleading tumor endpoint warning | Rule-Based tumor model construction always initialized/logged LLM credential state, so /simulation/tumor/test returned IO_SECRET_KEY missing in errors despite no active LLM worker or queen. | backend/nanobot_simulation.py | Verified by failing regression test and live endpoint response | Fixed; retested endpoint errors=[]
ISS-018 | API-005; CLI-001; CLI-002; CLI-003 | Documented entrypoints unavailable | README and quickstart documented uv run antelligence and uv run antelligence-api, but pyproject disabled package installation so uv could not spawn the scripts. | pyproject.toml; README.md; docs/QUICKSTART_TUMOR_SIM.md | Verified by uv run antelligence --help failing with no such file | Fixed; packaging enabled and uv run antelligence --help passes
ISS-019 | API-005; CLI-001; CLI-002 | Default basic runs used LLM mode | Packaged API shared config and CLI direct model construction omitted agent_type, causing basic local simulate/benchmark/API runs to fall back to LLM-Powered mode. | backend/config.py; backend/cli.py | Verified by API/CLI stdout logs containing IO_SECRET_KEY missing | Fixed; config and CLI pass agent_type=Rule-Based; real API/CLI retest has no missing-key warning

## Test Runs
Run ID | Date | Scope | Command or Browser Flow | Result | Errors Found | Artifacts | Notes
TR-001 | 2026-06-22 | Initial inventory | Code inspection only | Complete | 3 | Feature Stories + Error Log | Behavior testing starts after this workbook export.
TR-002 | 2026-06-22 | Frontend production build | npm --prefix frontend run build | Pass | 0 | Terminal output | Vite build succeeded; warning: bundle chunk exceeds 500 kB and Browserslist data is stale.
TR-003 | 2026-06-22 | Frontend lint | npm --prefix frontend run lint | Pass with warnings | 1 | Terminal output | 0 errors, 9 warnings. Logged as ISS-004.
TR-004 | 2026-06-22 | Backend import/start | UV_CACHE_DIR=/private/tmp/uv-cache uv run python -c 'import backend.main; print("import ok")'; uvicorn backend.main:app | Fail then pass | 1 | Terminal output | Fixed litellm_client import order; health endpoint returns healthy.
TR-005 | 2026-06-22 | CORS preflight | OPTIONS /simulation/run from Origin http://127.0.0.1:8081 | Fail then pass | 1 | curl output | Fixed 8081 localhost and 127.0.0.1 origins.
TR-006 | 2026-06-22 | Ant Colony entry + history | Browser: enter Ant Colony; observe HistoricalPerformance | Fail then pass | 1 | Playwright console/snapshot | Fixed stats.map crash by restoring synchronous localStorage history helpers.
TR-007 | 2026-06-22 | Ant simulation API fast path | POST /simulation/run Rule-Based blockchain_enabled=false | Fail then pass | 2 | curl output | Fixed blockchain opt-in and food double-counting; returns 13 steps, 15/15 food, 0 transactions.
TR-008 | 2026-06-22 | Ant Colony browser happy path | Browser: Ant Colony -> Agent Configuration -> Rule-Based -> Run Simulation | Pass | 0 | Playwright eval/console | Fresh retest: 0 console warnings/errors, history saved 15 food over 13 steps, blockchain inactive.
TR-009 | 2026-06-22 | Ant timeline scrubber | Browser: click ant simulation timeline slider after run | Fail then pass | 1 | Playwright eval | Slider moves from Step 1 of 13 to Step 7 of 13 and all visible counters align.
TR-010 | 2026-06-22 | Tumor simulation browser run | Browser: /tumor -> Rule-Based -> disable LLM queen -> Run Simulation | Fail then pass | 1 | Playwright console/eval | Fixed sessionStorage quota handling; tumor result loads with no console warnings/errors.
TR-011 | 2026-06-22 | Tumor timeline scrubber | Browser: click tumor timeline slider after run | Fail then pass | 1 | Playwright eval | Slider moves from Step 1/200 to Step 101/200 and persists tumorSimulationStep=100.
TR-012 | 2026-06-22 | Intro navigation | Browser: / -> inspect buttons; press Enter; click Tumor; click Tumor Hunt | Pass | 0 | Playwright console/eval | Intro has three entry buttons; Enter opens Ant Colony; Tumor routes to /tumor; Hunt routes to /tumor-hunt.
TR-013 | 2026-06-22 | Comparison guard and fast path | Browser: /comparison -> no agent guard -> one Rule-Based batch | Fail then pass | 3 | Playwright eval/backend logs | Fixed empty-agent guard, config mutation during run, and blockchain_enabled=true slow path; one-run retest produced 10 food, 19 steps, 0ms latency.
TR-014 | 2026-06-22 | Comparison CSV export | Browser: intercept Export CSV generated blob | Pass | 0 | Playwright eval | Export generated simulation-comparison timestamped CSV with expected 10F-5A-Rule-Based row.
TR-015 | 2026-06-22 | 404 fallback | Browser: /definitely-missing-route | Fail then pass | 1 | Playwright console/eval | Fallback rendered 404 and home link; console error downgraded to debug and retested with 0 warnings/errors.
TR-016 | 2026-06-22 | Tumor Hunt run and stats | Browser: /tumor-hunt -> Run Hunt | Pass | 0 | Playwright console/eval/backend logs | Default Rule-Based hunt completed 34/34 cells killed, showed wave notification/live stats, and had 0 console warnings/errors.
TR-017 | 2026-06-22 | Tumor Hunt playback | Browser: wait for final summary, click playback scrubber | Pass | 0 | Playwright eval | Autoplay reached 107/107 final summary; scrubber moved to 54/107 and paused.
TR-018 | 2026-06-22 | Ant configuration and analysis cluster | Browser: Rule-Based ants + heuristic queen + Rule-Based predators + blockchain off -> /simulation/run | Fail then pass | 3 | Playwright network/eval/console | Run returned 18 steps, 15/15 food, 6 caught ants, 0 API calls, 0 blockchain transactions; fixed predator copy, chart copy, and pheromone toggle label.
TR-019 | 2026-06-22 | Ant slider keyboard isolation | Browser: focus Territory Width slider, press ArrowRight | Fail then pass | 1 | Playwright keyboard/eval | Before fix, ArrowRight changed slider and advanced playback; after fix, width changed 16->17 while step stayed 2/18.
TR-020 | 2026-06-22 | Ant Queen comparison | Browser: click Run Queen Comparison | Pass | 0 | Playwright network/snapshot | /simulation/compare returned 15 no-queen vs 15 with-queen; cards, chart, and analysis rendered with 0 console warnings/errors.
TR-021 | 2026-06-22 | Preview mode guardrails | Vite --mode preview on :8082; browser run attempts on Ant, Comparison, Tumor, Hunt | Pass | 0 | Playwright network/eval/console; npm build:preview | Preview banner and per-page checkpoints rendered; Ant/Comparison/Tumor/Hunt run buttons made no /simulation or :8001 requests; preview build passed.
TR-022 | 2026-06-22 | Tumor setup and config payload | Browser: expand tumor config, edit Domain Size, switch Rule-Based, disable Queen, run simulation | Fail then pass | 1 | Playwright network/eval/console | Found hidden use_llm_queen=true after Queen disabled; fixed sidebar state. Retest sent domain_size=650, Rule-Based, use_queen=false, use_llm_queen=false, max_steps=200.
TR-023 | 2026-06-22 | Tumor visualization tabs and legend | Browser: after tumor run click Detailed Mode and Chemokine tab | Pass | 0 | Playwright eval/console | Substrate labels Oxygen/Drug/IFN/TNF/Perforin/Chemokine rendered; Visualization Legend showed Nanobots, Tumor Cells, Blood Vessels, Hypoxic Regions; 0 warnings/errors.
TR-024 | 2026-06-22 | Tumor backend endpoint cluster | curl /simulation/tumor/test, /performance, /compare, /compare-ced with small Rule-Based configs | Fail then pass | 1 | curl output; pytest regression | Fixed tumor model LLM-client gate. Retest: /tumor/test status success, 10 steps, errors=[], performance/compare/CED returned kill metrics and substrate summaries.
TR-025 | 2026-06-22 | Simulation cache/history endpoints | curl POST /simulation/cache twice; GET /simulation/history; GET filtered history; GET /simulation/compare/{id1}/{id2} | Pass | 0 | curl output; cache files | Cached ant and tumor payloads; files existed; history contained new IDs; tumor filter returned only tumor rows; compare returned simulation1/simulation2 and numeric differences.
TR-026 | 2026-06-22 | Packaged API entrypoint | ANTELLIGENCE_RUN_DB=/private/tmp/... uv run antelligence-api; curl /health, /simulate, /runs/{run_id} | Fail then pass | 2 | uv/curl/server output; pytest | Fixed packaging and Rule-Based default. Retest: health ok/run_store_ready, simulate completed with kill_rate, /runs retrieved same ID, temp SQLite DB existed, no missing-key warning.
TR-027 | 2026-06-22 | CLI advertised commands | uv run antelligence --help; simulate; benchmark; leaderboard | Fail then pass | 3 | uv output; JSON artifacts | Fixed package entrypoint and CLI Rule-Based default. Retest: help described CLI, simulate JSON has config/metrics/errors=[], benchmark produced 2 results, leaderboard exited 0 with offline fallback, stdout had no IO_SECRET_KEY warning.
TR-028 | 2026-06-22 | Backend/CLI regression suite | UV_CACHE_DIR=/private/tmp/uv-cache uv run --extra test pytest tests/test_cli.py tests/test_config.py tests/test_api_server.py tests/test_nanobot.py -q | Pass | 0 | pytest output | 67 passed after packaging, Rule-Based default, and tumor LLM-client gate fixes.